## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BHANDARKHALI Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002693/2021-2022 | 235/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
2 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BHANDARKHALI Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002694/2021-2022 | 236/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3 | NORTH 24 PARGANAS | Hingalganj | Eastern Mechanical | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I and II under Bhandarkhali WS Scheme Block-Hingalganj New District of 24 Pgs. N |  |  | ORD/001217/2023-2024 | 4873/EMD | 14/08/2023 | 13/09/2023 | DEBJYOTI BASU | 20.59 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Hingalganj | Eastern Mechanical | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No. III under Bhandarkhali WS Scheme Block-Hingalganj New District of 24 Pgs.N |  |  | ORD/001218/2023-2024 | 4874/EMD | 14/08/2023 | 13/09/2023 | DAS ENTERPRISE (BARANAGAR) | 10.3 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No- 2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Bhandarkhali water supply scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000725/2023-2024 | 2512/BD | 22/08/2023 | 22/08/2024 | M/S NIRMAN CONSTRUCTION. | 521.98 | 270.1 | 51.75 | 60
6 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Material Requisition To Resource Division |  |  | RTOR000231/2022-2023 | 869/BD | 22/03/2023 | 22/03/2023 | Resource Division | 45.98 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Bhanderkhali w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001983/2023-2024 | 918/BD | 15/03/2024 | 14/05/2024 | SAHA CONSTRUCTION & CO | 77.65 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Bhandarkhali Piped Water Supply Scheme | SM/15827 | New | Acceptance cum work order for Sinking of 1 No. 400.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe and strainers at T/W site-1 for Bhanderkhali w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/000062/2025-2026 | 845-HSD | 19/05/2025 | 29/05/2025 | M/S NIRMAN CONSTRUCTION. | 4.15 | 0 | 0 | 0
Total | [13 empty] | 690.29 | 279.76 | 40.53