## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002698/2021-2022 | 240/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.6 | 3.6 | 100 | 0
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002697/2021-2022 | 239/HSD | 02/02/2022 | 17/02/2022 | UMWELT ENGINEER PVT.LTD. | 4.83 | 4.83 | 100 | 0
3 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 15.28 | 0.07 | 11
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Atpukur W/S Scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000851/2023-2024 | 2616/BD | 29/08/2023 | 29/08/2026 | M/S PROGATI ENTERPRISE. | 461.22 | 166.52 | 36.1 | 37
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Material Requisition To Resource Division |  |  | RTOR000224/2022-2023 | 875/BD | 22/03/2023 | 22/03/2023 | Resource Division | 28.4 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-I). | Assistant Engineer | Junior Engineer | ORD/001919/2023-2024 | 291/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.87 | 0 | 0 | 100
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-F). | Assistant Engineer | Junior Engineer | ORD/001939/2023-2024 | 267/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-I). | Assistant Engineer | Junior Engineer | ORD/001905/2023-2024 | 277/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
9 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-J). | Assistant Engineer | Junior Engineer | ORD/001906/2023-2024 | 278/HSD | 06/03/2024 | 16/03/2024 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
10 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-G). | Assistant Engineer | Junior Engineer | ORD/001917/2023-2024 | 289/HSD | 06/03/2024 | 16/03/2024 | S.M.TRADERS. | 0.87 | 0 | 0 | 100
11 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-B). | Assistant Engineer | Junior Engineer | ORD/001940/2023-2024 | 258/HSD | 06/03/2024 | 16/03/2024 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
12 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-G). | Assistant Engineer | Junior Engineer | ORD/001941/2023-2024 | 270/HSD | 06/03/2024 | 16/03/2024 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
13 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-C). | Assistant Engineer | Junior Engineer | ORD/001911/2023-2024 | 283/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
14 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-F). | Assistant Engineer | Junior Engineer | ORD/001915/2023-2024 | 287/HSD | 06/03/2024 | 16/03/2024 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
15 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-A). | Assistant Engineer | Junior Engineer | ORD/001934/2023-2024 | 256/HSD | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
16 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-D). | Assistant Engineer | Junior Engineer | ORD/001937/2023-2024 | 263/HSD | 06/03/2024 | 16/03/2024 | S.M.TRADERS. | 0.88 | 0.88 | 100 | 100
17 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-E). | Assistant Engineer | Junior Engineer | ORD/001938/2023-2024 | 265-HSD. | 06/03/2024 | 16/03/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
18 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Quotation for Service Connection Charges for PH- II, Zone- I under Atpukur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05537/2023-2024 | BP-365-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.6 | 0 | 0 | 0
19 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Service connection charges at PH-I under Atpukur W/S Scheme |  |  | BILL/04754/2023-2024 | BP-293-23-24 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 24.93 | 0 | 0 | 0
20 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme | SM/15828 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Atpukur (Z-I) and Uchildaha w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001497/2024-2025 | 633/BD | 28/02/2025 | 14/04/2025 | SHIBU BISWAS. | 51.76 | 0 | 0 | 0
Total | [13 empty] | 21929.62 | 197.24 | 0.9