## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002741/2021-2022 | 337/HSD | 21/02/2022 | 08/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.83 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002742/2021-2022 | 338/HSD | 21/02/2022 | 08/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 0 | 0 | 1
3 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/002743/2021-2022 | 347/HSD | 21/02/2022 | 08/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.72 | 0 | 0 | 1
4 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Material Requisition To Resource Division |  |  | RTOR000233/2022-2023 | 870/BD | 22/03/2023 | 22/03/2023 | Resource Division | 51.83 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Service connection charges at PH-I under Khariat W/S Scheme |  |  | BILL/04752/2023-2024 | BP-291-23-24 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.04 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Quotation for Service Connection Charges for PH- II under Khariat Abad W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05539/2023-2024 | BP-366-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.11 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Quotation for Service Connection Charges for PH- III under Khariat Abad W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05535/2023-2024 | BP-367-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.04 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Sandeshkhali-I | Central Drilling | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 250 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Khariat Abad W/S Scheme, Sandeshkhali block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001202/2023-2024 | 4027/BD | 12/10/2023 | 11/10/2025 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 618.97 | 0 | 0 | 50
10 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Khariat Abad Piped Water Supply Scheme | SM/15829 | New | Formal work order for Withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Bangali para, near cyclone centre, Sahaji para, shayam molla para, Barik para, Ghorami para etc of Jhupkhali and Nazat BDO office, Metekhali, Parsemari & other tail end areas of Boyermari Abad to improve functionality under Khariat Abad w/s scheme under Hasnabad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2025-2026 | 1749/BD | 28/05/2025 | 25/09/2025 | CHANCHAL ENTERPRISE & CO. | 177.38 | 0 | 0 | 0
Total | [13 empty] | 22216.5 | 0 | 0