## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Petua Dhanihati Piped Water Supply Scheme | SM/15830 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PETUA DHANIHATI Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002746/2021-2022 | 350/HSD | 21/02/2022 | 08/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
2 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Petua Dhanihati Piped Water Supply Scheme | SM/15830 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PETUA DHANIHATI Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002747/2021-2022 | 351/HSD | 21/02/2022 | 08/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.51 | 4.51 | 100 | 1
3 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Petua Dhanihati Piped Water Supply Scheme | SM/15830 | New | Material Requisition To Resource Division |  |  | RTOR000227/2022-2023 | 879/BD | 22/03/2023 | 22/03/2023 | Resource Division | 23.37 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Petua Dhanihati Piped Water Supply Scheme | SM/15830 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Petua Dhanihati W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000564/2024-2025 | 1004/HSd | 29/08/2024 | 08/09/2024 | S.K.ENTERPRISE. | 0.9 | 0 | 0 | 100
5 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Petua Dhanihati Piped Water Supply Scheme | SM/15830 | New | Service connection charges at PH-I under Petuadhanihati W/S Scheme |  |  | BILL/04755/2023-2024 | BP-292-23-24 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.12 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Petua Dhanihati Piped Water Supply Scheme | SM/15830 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Petua Dhanihati W/S Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000901/2023-2024 | 2705/BD | 04/09/2023 | 04/09/2026 | M/S NIRMAN CONSTRUCTION. | 379.24 | 219.83 | 57.97 | 70
Total | [13 empty] | 416.96 | 229.17 | 54.96