## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ambaria Piped Water Supply Scheme | SM/15831 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (AMBARIA Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002691/2021-2022 | 233/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
2 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ambaria Piped Water Supply Scheme | SM/15831 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (AMBARIA Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002692/2021-2022 | 234/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.29 | 4.29 | 100 | 1
3 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ambaria Piped Water Supply Scheme | SM/15831 | New | Material Requisition To Resource Division |  |  | RTOR000230/2022-2023 | 881/BD | 22/03/2023 | 22/03/2023 | Resource Division | 24.21 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Hingalganj | Eastern Mechanical | Ambaria Piped Water Supply Scheme | SM/15831 | New | Quotation for Service Connection Charges for PH- I under Amberia W/S Scheme in the district of North 24 Pgs. JL No- 94, Plot No. 339 |  |  | BILL/04868/2023-2024 | BP-329-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.19 | 0 | 0 | 0
5 | NORTH 24 PARGANAS | Hingalganj | Eastern Mechanical | Ambaria Piped Water Supply Scheme | SM/15831 | New | Quotation for Service Connection Charges for PH- II under Amberia W/S Scheme in the district of North 24 Pgs. J.L. No.-94, Plot No- 319 |  |  | BILL/04873/2023-2024 | BP-330-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.21 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Hingalganj | Central Drilling | Ambaria Piped Water Supply Scheme | SM/15831 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 107.12 | 0.5 | 11
7 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ambaria Piped Water Supply Scheme | SM/15831 | New | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, leftout work of 500 cum reservoir in connection with Augmentation of Chandpur w/s scheme (Z-II), Hasnabad Block, Construction of Protection wall for protection of UPVC distribution pipe line, Construction of approach road Zone-5 of Surfaced based w/s scheme Hasnabad, Protection works in different location of Amberia and Ghuni mouza, 2 nos. pump connection at PH No.-1 & 2 with CWR in connection within Amberia water supply scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2025-2026 | 1748/BD | 28/05/2025 | 27/07/2025 | M/S DATTA ENTERPRISE. | 102.67 | 0 | 0 | 80
8 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ambaria Piped Water Supply Scheme | SM/15831 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR, pipe connection and cost of pipes specials for Amberia W/S Scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 1737/BD | 08/06/2023 | 08/06/2025 | MONDAL & CO. (BASIRHAT). | 411.21 | 339.67 | 82.6 | 96
Total | [13 empty] | 21897.38 | 455.9 | 2.08