## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002722/2021-2022 | 287/HSD | 10/02/2022 | 25/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.44 | 3.44 | 100 | 0
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002721/2021-2022 | 284/HSD | 09/02/2022 | 24/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
3 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Kusangra Piped Water Supply Scheme | SM/15832 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Kusangra W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000898/2023-2024 | 2703/BD | 04/09/2023 | 04/09/2026 | M/S PROGATI ENTERPRISE. | 439.52 | 167.09 | 38.02 | 20
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Material Requisition To Resource Division |  |  | RTOR000208/2022-2023 | 893/BD | 22/03/2023 | 22/03/2023 | Resource Division | 45.01 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Over Head Reservoir site (HW site) for Kusangra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001811/2023-2024 | 676/BD | 01/03/2024 | 06/12/2024 | M/S GHOSH CONSTRUCTION. | 8.58 | 7.78 | 90.6 | 90
7 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 3477/BD | 10/12/2024 | 10/12/2024 | Resource Division | 25.32 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Kusangra Piped Water Supply Scheme | SM/15832 | New | New Service Connection at PH-III under Kusangra W/S Scheme. |  |  | BILL/04124/2023-2024 | BP-261-23-24 | 02/01/2024 | 02/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.6 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Kusangra Piped Water Supply Scheme | SM/15832 | New | Quotation for Service Connection Charges for PH- II under Kusangra W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05531/2023-2024 | BP-369-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.5 | 0 | 0 | 0
10 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Kusangra Piped Water Supply Scheme | SM/15832 | New | Supplementary Quotation for Location Changes for PH- III under Kusangra W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05530/2023-2024 | BP-368-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.99 | 0 | 0 | 0
11 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No- 1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kusangra w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001502/2024-2025 | 632/BD | 28/02/2025 | 29/04/2025 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.49 | 0 | 0 | 0
12 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Kusangra Piped Water Supply Scheme | SM/15832 | New | Dhuturdah Health Center Road from 0.00Km to 6.50Km restoration work of damages caused/to be caused by due to laying of pipe line by Barasat Division, PHE Dte.on existing black top surface, paver block surface and hard shoulder under Barasat Highway Divin-I PWRD in the District of North 24 Parganas |  |  | BILL/01142/2025-2026 |  | 08/08/2025 | 08/08/2025 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 140.85 | 0 | 0 | 0
Total | [13 empty] | 22101.9 | 183.14 | 0.83