## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KETARCHAK Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002695/2021-2022 | 237/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 1
2 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KETARCHAK Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002696/2021-2022 | 238/HSD | 02/02/2022 | 17/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3 | NORTH 24 PARGANAS | Hingalganj | Central Drilling | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Ketarchak water supply scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000724/2023-2024 | 2615/BD | 29/08/2023 | 29/08/2024 | MONDAL PRECISION PVT.LTD | 507.61 | 75.88 | 14.95 | 30
5 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Material Requisition To Resource Division |  |  | RTOR000229/2022-2023 | 878/BD | 22/03/2023 | 22/03/2023 | Resource Division | 42.93 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) & PH No-1 (Size-3.60x3.00 mtr.) for Kalitala w/s scheme (Z-I), Hingalganj Block under Ketarchak Piped Water Supply Scheme within Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2024-2025 | 2959/BD | 04/10/2024 | 03/12/2024 | MD.SALIM GAZI. | 21.3 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No- 1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Ketarchak w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001501/2024-2025 | 634/BD | 28/02/2025 | 29/04/2025 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.48 | 0 | 0 | 0
8 | NORTH 24 PARGANAS | Hingalganj | Barasat Division | Ketarchak Piped Water Supply Scheme | SM/15833 | New | Acceptance cum work order for Sinking of 1 No. 400.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe and strainers at T/W site-1 for Ketarchak w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. |  |  | ORD/000061/2025-2026 | 844/HSD | 19/05/2025 | 29/05/2025 | M/S GHOSH CONSTRUCTION. | 3.39 | 0 | 0 | 0
Total | [13 empty] | 22002.13 | 85.53 | 0.39