## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BARGAN GOPALPUR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002702/2021-2022 | 247/HSD | 03/02/2022 | 18/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | Material Requisition To Resource Division |  |  | RTOR000204/2022-2023 | 890/BD | 22/03/2023 | 22/03/2023 | Resource Division | 46.13 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | New service connection for Bargan Gopalpur PH-I, Bargan Gopalpur minakhan |  |  | BILL/04047/2023-2024 | BP-253-23-24 | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.97 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | Acceptance cum work order for Strengthening of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No 2 within Bargan Gopalpur w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000910/2023-2024 | 2732/BD | 07/09/2023 | 14/09/2023 | GIRIDHARI DAS | 5 | 0 | 0 | 100
5 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | Acceptance cum work order for Strengthening of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No-1 within Bargan Gopalpur w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000880/2023-2024 | 2715/BD | 05/09/2023 | 15/09/2023 | PRITAM MUKHOPADHYAY. | 8.46 | 0 | 0 | 100
6 | NORTH 24 PARGANAS | Minakhan | Eastern Mechanical | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | New Service Connection at PH-II under Bargan Gopalpur W/S Scheme |  |  | BILL/04123/2023-2024 | BP-262-23-24 | 02/01/2024 | 02/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.84 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Minakhan | Central Drilling | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS | Minakhan | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme | SM/15902 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Bargan Gopalpur w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000147/2023-2024 | 1707/BD | 08/06/2023 | 09/06/2025 | M/S PROGATI ENTERPRISE. | 403.93 | 0 | 0 | 100
Total | [13 empty] | 21817.92 | 0 | 0