## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC | SM/17408 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I and II Rep. under Rajapur Block Baduria WS Scheme District of 24 Pgs. N |  |  | ORD/001215/2023-2024 | 4872/EMD | 14/08/2023 | 13/09/2023 | S.G. TECHNICAL SERVICES | 26.07 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC | SM/17408 | Augmentation | Route Survey, Design Drawing & DPR Preparation for RAJAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001984/2021-2022 | 356/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 4.13 | 99.34 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC | SM/17408 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1279/BD | 25/04/2023 | 25/04/2023 | Resource Division | 66.17 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC | SM/17408 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under RAJAPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 1608/EMD | 26/04/2023 | 02/01/2025 | A.S. ENTERPRISE | 18.91 | 17.92 | 94.79 | 40
Total | [13 empty] | 115.3 | 22.05 | 19.12