## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | SM/17409 | Augmentation | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Taranipur Water Supply Scheme Zone - II at Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2022-2023 | 1176/BD | 19/04/2022 | 18/07/2022 | UTPAL CONSTRUCTION & CO. | 137.41 | 25.64 | 18.66 | 13
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | SM/17409 | Augmentation | Route Survey, Design Drawing & DPR Preparation for TARANIPUR ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002513/2021-2022 | 447 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.4 | 3.4 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | SM/17409 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1261/BD | 25/04/2023 | 25/04/2023 | Resource Division | 17.18 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | SM/17409 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Taranipur zone - II W/S Scheme including increasing the height of back wash water tank at Swarupnagar Block under Basirhat Sub Division, PHE Dte. Capacity- 50.00 Cum/hr. | Assistant Engineer |  | ORD/002023/2023-2024 | 894/BD | 15/03/2024 | 14/05/2024 | M/S R.K. ENTERPRISE | 18.02 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | SM/17409 | Augmentation | Regarding Restoration charges for road damages. |  |  | BILL/03467/2023-2024 | BP-2023-24-830 | 15/03/2024 | 15/03/2024 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 40.09 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC | SM/17409 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21555.87 | 29.04 | 0.13