## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1267/BD | 25/04/2023 | 25/04/2023 | Resource Division | 99.41 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 4020/BD | 12/10/2023 | 12/10/2023 | Resource Division | 17.25 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Formal work order for Construction of 450cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing FHTC for Augmentation of Deara water supply Scheme under Barasat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000760/2023-2024 | 2561/BD | 24/08/2023 | 24/08/2024 | SINGHA ROY & CO. | 507.92 | 103.06 | 20.29 | 25
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at Deara Water Supply Scheme under Barasat-II Block, under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000569/2024-2025 | 3081/BD | 29/10/2024 | 28/11/2024 | M/S SANJAY ADHIKARI | 32.14 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Preparation of DPR in connection of augmentation of Deara Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-21 | Assistant Engineer | Junior Engineer | ORD/000314/2022-2023 | 568/BSD | 29/06/2022 | 29/07/2022 | RADIANT | 2.97 | 2.79 | 93.88 | 100
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Payment of invoice bill for new service connection at p/h no: III under Deara water supply scheme. |  |  | BILL/04751/2023-2024 | BP-290-23-24 | 27/02/2024 | 27/02/2024 | W.B.S.E.D.C.L. (GANGANAGAR C.C.C.) | 3.79 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Acceptance cum work order for Additional Laying of UPVC pipe line and allied work in connection with Augmentation Deara Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001048/2024-2025 | 53/BD | 07/01/2025 | 06/02/2025 | SINGHA ROY & CO. | 27.35 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Deara Water Supply Scheme within Barasat-II Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001156/2024-2025 | 375/BD | 04/02/2025 | 16/03/2025 | TALUKDER & CO. | 9.19 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC | SM/17679 | Augmentation | Construction of Pump House with latrine at Deara water Supply Scheme under Barasat-II Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. |  | Junior Engineer | ORD/001383/2024-2025 | 1021/BSD | 03/01/2025 | 12/02/2025 | M.ENTERPRISE. | 4.87 | 0 | 0 | 0
Total | [13 empty] | 22044.65 | 105.85 | 0.48