## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME | SM/17680 | Augmentation | Route Survey, Design Drawing & DPR Preparation for TYANTRA NEORA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001948/2021-2022 | 204/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.94 | 2.51 | 85.35 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME | SM/17680 | Augmentation | Formal work order for Providing FHTC including laying of Pipe Line, Renovation of Filter Media, Repairing of Wooden Jetty and Electro Mechanical Work for Augmentation at Tyantra Neora pond based water supply scheme in Basirhat - II Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000233/2023-2024 | 1738/BD | 08/06/2023 | 06/09/2023 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 88.36 | 20.62 | 23.34 | 30
Total | [13 empty] | 91.31 | 23.14 | 25.34