## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Carriage of Field Test Kit (FTK) and Data Reporting Sheet (DRS)Phase-III including loading & unloading from Barasat Division Office to respective BMOH Office in North 24 Parganas District related to Water Quality Surveillance Programme under Jal Jeevan Mission. |  | Junior Engineer | ORD/000288/2024-2025 | 749/BST | 04/07/2024 | 11/07/2024 | M/S R.B.S.ENTERPRISE. | 0.93 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Acceptance cum work order for Uploading of FTK Data Sheet (Phase-II) to WQMIS related to Water Quality Monitering & Surveillance Programme under Jal Jeevan Mission of North 24 parganas. | Assistant Engineer |  | ORD/001754/2023-2024 | 445/BD | 12/02/2024 | 12/03/2024 | M/S B.K.ENTERPRISE. | 6.85 | 3.42 | 49.99 | 50
3 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Acceptance cum work order for Collection of Water Sample in uninterrupted manner and submit the same to the respective PHED laboratory by engagement of agency where ever facilitator are not available, unwilling or inactive in North 24 Pargaanas District under Barasat Division, PHE Dte.(Phase-II). | Assistant Engineer |  | ORD/001755/2023-2024 | 444/BD | 12/02/2024 | 12/03/2024 | M/S B.K.ENTERPRISE. | 7.83 | 7.76 | 99.17 | 49
4 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Water Sample testing awareness generation charges of ASAHs through FTK |  |  | BILL/01245/2024-2025 | C102413443387 | 04/10/2024 | 04/10/2024 | DH & FWS NORTH 24 PGS. | 2.9 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Regarding water sample testing and awareness generation charges of ASHS's through FTK for the financial year 2022-23 in favour of Basirhat Health District |  |  | BILL/03294/2023-2024 | BP-2023-24-764 | 15/02/2024 | 15/02/2024 | BASIRHAT HEALTH DISTRICT. | 15.24 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Regarding water sample testing and awareness generation charges of ASHA's through FTK for the financial year 2022-23 in favour of North 24 Parganas Health District. |  |  | BILL/03296/2023-2024 | BP-2023-24-763 | 15/02/2024 | 15/02/2024 | DH & FWS NORTH 24 PGS. | 14.57 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Water Sample testing awareness generation charges of ASAHs through FTK |  |  | BILL/01179/2024-2025 | BP-2024-25-401 | 04/10/2024 | 04/10/2024 | BASIRHAT HEALTH DISTRICT. | 4.06 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Regarding water sample testing & awareness generation charges of ASHAs' through FTK for September 2024 to March 2026 of Basirhat Health District |  |  | BILL/00605/2026-2027 |  | 26/05/2026 | 26/05/2026 | BASIRHAT HEALTH DISTRICT. | 7.21 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) | SM/18143 | Support-WQMSP | Regarding water sample testing & awareness generation charges of ASHAs' through FTK for September 2024 to March 2026 of North 24 Parganas Health District |  |  | BILL/00604/2026-2027 |  | 26/05/2026 | 26/05/2026 | DH & FWS NORTH 24 PGS. | 9.99 | 0 | 0 | 0
Total | [13 empty] | 69.56 | 11.18 | 16.08