## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Work order for Supply of Chemicals, Glass Ware and accessories for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000026/2023-2024 | 1231/BD | 24/04/2023 | 24/05/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 56.46 | 0 | 0 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. |  |  | BILL/00947/2023-2024 | BP-2023-24-375 | 20/09/2023 | 20/09/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. |  |  | BILL/01601/2023-2024 | BP-2023-24-506 | 17/10/2023 | 17/10/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. |  |  | BILL/01974/2023-2024 | BP-2023-24-519 | 07/11/2023 | 07/11/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. |  |  | BILL/01978/2023-2024 | BP-2023-24-516 | 07/11/2023 | 07/11/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. |  |  | BILL/01977/2023-2024 | BP-2023-24-518 | 07/11/2023 | 07/11/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. |  |  | BILL/01975/2023-2024 | BP-2023-24-517 | 07/11/2023 | 07/11/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. |  |  | BILL/01473/2023-2024 | BP-2023-24-419 | 11/10/2023 | 11/10/2023 | YOUTH DEVELOPMENT CENTER | 0.16 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. |  |  | BILL/01474/2023-2024 | BP-2023-24-419 | 11/10/2023 | 11/10/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.11 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the month of August'23. |  |  | BILL/00946/2023-2024 | BP-2023-24-375 | 20/09/2023 | 20/09/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. |  |  | BILL/01598/2023-2024 | BP-2023-24-507 | 17/10/2023 | 17/10/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. |  |  | BILL/01973/2023-2024 | BP-2023-24-520 | 07/11/2023 | 07/11/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. |  |  | BILL/00949/2023-2024 | BP-2023-24-375 | 20/09/2023 | 20/09/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. |  |  | BILL/01600/2023-2024 | BP-2023-24-504 | 17/10/2023 | 17/10/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. |  |  | BILL/01470/2023-2024 | BP-2023-24-419 | 11/10/2023 | 11/10/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.16 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. |  |  | BILL/01604/2023-2024 | BP-2023-24-502 | 17/10/2023 | 17/10/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. |  |  | BILL/02963/2023-2024 | BP-2023-24-622 | 20/12/2023 | 20/12/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. |  |  | BILL/02962/2023-2024 | BP-2023-24-621 | 20/12/2023 | 20/12/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. |  |  | BILL/00948/2023-2024 | BP-2023-24-375 | 20/09/2023 | 20/09/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. |  |  | BILL/01599/2023-2024 | BP-2023-24-503 | 17/10/2023 | 17/10/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. |  |  | BILL/01603/2023-2024 | BP-2023-24-505 | 17/10/2023 | 17/10/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
22 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. |  |  | BILL/01472/2023-2024 | BP-2023-24-419 | 11/10/2023 | 11/10/2023 | BITHARI DISHA. | 0.16 | 0 | 0 | 0
23 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. |  |  | BILL/02965/2023-2024 | BP-2023-24-620 | 20/12/2023 | 20/12/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
24 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. |  |  | BILL/01997/2023-2024 | BP-2023-24-520 | 07/11/2023 | 07/11/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
25 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. |  |  | BILL/01471/2023-2024 | BP-2023-24-419 | 11/10/2023 | 11/10/2023 | PATHER PANCHALI SEVA SAMITY. | 0.16 | 0 | 0 | 0
26 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. |  |  | BILL/00951/2023-2024 | BP-2023-24-375 | 20/09/2023 | 20/09/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
27 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. |  |  | BILL/01475/2023-2024 | BP-2023-24-419 | 11/10/2023 | 11/10/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.16 | 0 | 0 | 0
28 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. |  |  | BILL/00950/2023-2024 | BP-2023-24-375 | 20/09/2023 | 20/09/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
29 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Acceptance cum work order for Engagement of 16 personnel (2 nos. Chemist, 2 nos. Bacteriologist, 1 no. AAS Operator, 2 nos. Laboratory Assistant,4 nos. Sampling Assistant & 5 nos. Lab Attendent ) in different water testing laboratories under Barasat Division,PHE Dte. (North 24 Pargansa District Lab, Hingalganj Sub-District Lab, Bodai Sub-District Lab., Bagda Sub-District Lab, Chandpara Sub-District Lab, Habra Sub-District Lab, Basirhat Sub-Division Lab ) for 1(one)year (Effect from 01.01.2023 to 31.12.2023.) | Assistant Engineer |  | ORD/001028/2022-2023 | 185/BD | 19/01/2023 | 19/01/2024 | M/S B.K.ENTERPRISE. | 36.04 | 0 | 0 | 65
30 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Procurement of Hot Air Oven and Thermometer-Hygrometer-Clock including demonstration & calibration of the instrument at North 24 Parganas District Water Testing laboratory under Barasat Division, PHE Dte. |  | Junior Engineer | ORD/001733/2023-2024 | 1052/BST | 17/11/2023 | 24/11/2023 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.49 | 0 | 0 | 85
31 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Acceptance cum work order for Chemicals & glassware for different water testing laboratories for 6 (Six) months related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001952/2023-2024 | 844/BD | 13/03/2024 | 12/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 76.15 | 0 | 0 | 95
32 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 |  |  | BILL/03082/2023-2024 | BP-2023-24-677 | 10/01/2024 | 10/01/2024 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
33 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. |  |  | BILL/03438/2023-2024 | BP-2023-24-838 | 15/03/2024 | 15/03/2024 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
34 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. |  |  | BILL/03443/2023-2024 | BP-2023-24-833 | 15/03/2024 | 15/03/2024 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
35 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. |  |  | BILL/03440/2023-2024 | BP2023-24-835 | 15/03/2024 | 15/03/2024 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
36 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance March-2024. |  |  | BILL/00044/2024-2025 |  | 12/04/2024 | 12/04/2024 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 |  |  | BILL/03083/2023-2024 | BP-2023-24-675 | 10/01/2024 | 10/01/2024 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
38 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. |  |  | BILL/03300/2023-2024 | BP-2023-24-768 | 15/02/2024 | 15/02/2024 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
39 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | remuneration of Laboratory Personnel & lab maintenance on month of December 23 |  |  | BILL/03081/2023-2024 | BP-2023-24-674 | 10/01/2024 | 10/01/2024 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
40 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024 |  |  | BILL/03441/2023-2024 | BP-2023-24-837 | 15/03/2024 | 15/03/2024 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
41 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. |  |  | BILL/03305/2023-2024 | BP-2023-24-769 | 15/02/2024 | 15/02/2024 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
42 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00045/2024-2025 | BP-2024-25-13 | 16/04/2024 | 16/04/2024 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
43 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 |  |  | BILL/03084/2023-2024 | BP-2023-24-676 | 10/01/2024 | 10/01/2024 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
44 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. |  |  | BILL/03303/2023-2024 | BP-2023-24-767 | 15/02/2024 | 15/02/2024 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
45 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024 |  |  | BILL/03442/2023-2024 | BP-2023-24-838 | 13/03/2024 | 13/03/2024 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
46 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. |  |  | BILL/03439/2023-2024 | BP-2023-24-834 | 15/03/2024 | 15/03/2024 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
47 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00047/2024-2025 | BP-2024-25-11 | 16/04/2024 | 16/04/2024 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
48 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 |  |  | BILL/03086/2023-2024 | BP-2023-24-678 | 10/01/2024 | 10/01/2024 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
49 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00046/2024-2025 | BP-2024-25-12 | 16/04/2024 | 16/04/2024 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
50 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel @lab maintenance on month of december 23 |  |  | BILL/03080/2023-2024 | BP-2023-24-673 | 10/01/2024 | 10/01/2024 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
51 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance |  |  | BILL/03299/2023-2024 | BP-2023-24-766 | 15/02/2024 | 15/02/2024 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
52 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. |  |  | BILL/03302/2023-2024 | BP-2023-24-770 | 15/02/2024 | 15/02/2024 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
53 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. |  |  | BILL/03304/2023-2024 | BP-2023-24-765 | 15/02/2024 | 15/02/2024 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
54 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00048/2024-2025 | BP-2024-25-10 | 16/04/2024 | 16/04/2024 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
55 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. |  |  | BILL/00111/2024-2025 | BP-2024-25-26 | 09/05/2024 | 09/05/2024 | IONET | 0.76 | 0 | 0 | 0
56 | NORTH 24 PARGANAS |  | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. | SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance March-2024. |  |  | BILL/00043/2024-2025 |  | 12/04/2024 | 12/04/2024 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
Total | [13 empty] | 193.26 | 0 | 0