## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 3090/BD | 10/10/2023 | 10/10/2023 | Resource Division | 7.26 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Sohai Swetpur Zone-I within Deganga Block under Barasat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001044/2024-2025 | 3703/BD | 26/12/2024 | 25/01/2025 | GIRIDHARI DAS | 12.8 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Preparation of DPR in connection of augumentation of Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000611/2022-2023 | 672/BSD | 30/08/2022 | 29/09/2022 | RADIANT | 3.28 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/001841/2023-2024 | 1117/BSD | 09/02/2024 | 13/02/2024 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | New service connection at P.H.No- III , Zone-I of Swetpur water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). |  |  | BILL/04865/2023-2024 | BP-331-23-24 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.2 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (Zone-I) (NEW) under Swethpur W/S Scheme, District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer,Junior Engineer (Mechanical) | ORD/001176/2023-2024 | 4804/EMD | 09/08/2023 | 01/10/2025 | P.P. CONCERN | 10.71 | 0 | 0 | 90
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Formal work order for Construction of 550cum capacity 20Mtr staging Height R.C.C. Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Swetpur Zone-I Water Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2382/BD | 10/08/2023 | 11/08/2025 | M/S BISWAS BROTHERS. | 461.4 | 0 | 0 | 55
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. | SM/18410 | Augmentation | Acceptance cum work order for Repair & Renovation work at Different site in connection with Augmentation of Sohai Swetpur, Zone-I Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002017/2024-2025 | 1026/BD | 28/03/2025 | 12/05/2025 | M/S S.HAQUE & CO. | 12.75 | 0 | 0 | 100
Total | [13 empty] | 21851.05 | 0 | 0