## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Zone-I) (Rep.) under Bodai W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_9) |  |  | ORD/001883/2023-2024 | 6727/EMD | 28/11/2023 | 28/12/2023 | S.G. ENTERPRISE | 13.13 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 3094/BD | 10/10/2023 | 10/10/2023 | Resource Division | 26.86 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Zone-II) (Rep.) under Bodai W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_10) |  |  | ORD/001884/2023-2024 | 6728/EMD | 28/11/2023 | 28/12/2023 | DEY ENTERPRISE | 13.15 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Preparation of DPR in connection of augumentation of Bodai Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | Assistant Engineer | Junior Engineer | ORD/000287/2022-2023 | 548/BSD | 29/06/2022 | 29/07/2022 | RADIANT | 3.7 | 3.32 | 89.85 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | Assistant Engineer | Junior Engineer | ORD/001838/2023-2024 | 1116./1/BSD | 09/02/2024 | 13/02/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/001836/2023-2024 | 1116/BSD | 09/02/2024 | 13/02/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 89
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 24.41 | 0.11 | 11
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Formal work order for Construction of 900 cum capacity 20mtr Height R.C.C Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Bodai Zone-I Water Supply Scheme under Barasat Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001196/2023-2024 | 3080/BD | 10/10/2023 | 01/10/2025 | PUSPA ENTERPRISE. | 1051.63 | 444.01 | 42.22 | 64
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 6 (six) months from w.e.f. 01.06.2024) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred & seventy five only) per day Excluding fuel. (Period for 01/06/2024 to 30/11/2024) | Assistant Engineer | Junior Engineer | ORD/000049/2024-2025 | 140/BSD | 28/05/2024 | 28/11/2024 | MADHAB CHANDRA DAS | 0.87 | 1.88 | 216.66 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Continuation work Order for Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 6 (six) months from w.e.f. 01.12.2022) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred & seventy five only) per day Excluding fuel. (From-01/12/2024 to 31/05/2025) |  | Junior Engineer | ORD/001021/2024-2025 | 827/BSD | 22/11/2024 | 22/05/2025 | MADHAB CHANDRA DAS | 0.86 | 0.69 | 80.31 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Bodai-I Water Supply Scheme under JJM programme in Amdanga block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2024-2025 | 2580/BD | 05/09/2024 | 04/12/2024 | A.P POWER & CONCRETE | 325.89 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Continuation work order for Hiring 1(One) No. Diesel Luxury Car on Daily basis for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. (For the Period from 01/06/2025 to 30/11/2025) |  | Junior Engineer | ORD/000171/2025-2026 | 175/BSD | 27/05/2025 | 26/11/2025 | MADHAB CHANDRA DAS | 0.87 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Formal work order for road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-I and Amdanga Block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2025-2026 | 1306/BD | 24/04/2025 | 22/08/2025 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 99.64 | 0 | 0 | 0
Total | [13 empty] | 22878.14 | 476.09 | 2.08