## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Additional Survey work for DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001986/2021-2022 | 358/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.31 | 0.28 | 90 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Route Survey, Design Drawing & DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001985/2021-2022 | 357/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1251/BD | 25/04/2023 | 25/04/2023 | Resource Division | 139.05 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery along with allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Magurali and P.H. No.- II under Chandipur W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001270/2023-2024 | 4935/EMD | 18/08/2023 | 17/09/2023 | SUNRISE ENGINEERING CORPORATION | 39.08 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Chandipur water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000597/2023-2024 | 2418/BD | 11/08/2023 | 25/06/2025 | H.I.ENTERPRISE. | 813.8 | 763.96 | 93.88 | 85
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Acceptance cum work order for Restoration of UPVC pipe line and FHTC due to damage of Pipeline and House Connection by WBSEDCL for laying Electric cable at Chandipur Taltala More towards Ghoragacha of Chandipur water Supply Scheme within Basirhat - I Block within Basirhat Sub-Division PHE Dte. under Barasat Division PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/002284/2024-2025 | 05/BHTSD | 02/01/2025 | 02/05/2025 | RAKESH ENTERPRISE. | 2.97 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Road Restoration work |  |  | BILL/00857/2024-2025 | BP-2024-25-277 | 17/09/2024 | 17/09/2024 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 76.63 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.38 | 0.03 | 11
Total | [13 empty] | 22416.54 | 776.57 | 3.46