## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Additional Survey work for DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001986/2021-2022 | 358/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.31 | 0.28 | 90 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Route Survey, Design Drawing & DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001985/2021-2022 | 357/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1251/BD | 25/04/2023 | 25/04/2023 | Resource Division | 139.05 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery along with allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Magurali and P.H. No.- II under Chandipur W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001270/2023-2024 | 4935/EMD | 18/08/2023 | 17/09/2023 | SUNRISE ENGINEERING CORPORATION | 39.08 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC | SM/18582 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.38 | 0.03 | 11
Total | [13 empty] | 21523.15 | 12.61 | 0.06