## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Route Survey, Design Drawing & Preparation of DPR for Kalupur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001315/2021-2022 | 122/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer |  | ORD/002738/2021-2022 | 314/HSD | 15/02/2022 | 02/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 100
3 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer |  | ORD/002739/2021-2022 | 315/HSD | 15/02/2022 | 02/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 100
4 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-C) | Assistant Engineer |  | ORD/002740/2021-2022 | 336/HSD | 21/02/2022 | 08/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 100
5 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Material Requisition To Resource Division |  |  | RTOR000226/2022-2023 | 872/BD | 22/03/2023 | 22/03/2023 | Resource Division | 296.35 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 3442/BD | 06/12/2024 | 06/12/2024 | Resource Division | 38.05 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Formal work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2,3,4 (Size-3.60x3.00 mtr),Laying of DI rising main and DI/UPVC distribution pipe line,Providing Functional Household Tap Connection,Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places,Construction of 450 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Dakshin Akhratala water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001208/2023-2024 | 4047/BD | 13/10/2023 | 08/10/2026 | M/S DATTA ENTERPRISE. | 753.32 | 382.2 | 50.74 | 80
8 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Acceptance cum work order for sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000892/2024-2025 | 3376/BD | 02/12/2024 | 31/01/2025 | M/S K.P.PAL. | 25.88 | 0 | 0 | 0
9 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Acceptance cum work order for Additional Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection for Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001414/2024-2025 | 144/BD | 13/01/2025 | 29/03/2025 | JESMINE ENTERPRISE. | 10.58 | 0 | 0 | 0
10 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I, II, III IV (New) under Dakshin Akhratala W/S scheme under Block_ Sandeshkhali-I Dist. - 24Pgs(N) under EMD, PHE Dte. [SM/18617] | Assistant Engineer | Junior Engineer | ORD/000193/2025-2026 | 1131/EMD | 04/06/2025 | 02/09/2025 | ESENCE ENGINEERING CONCERN | 57.63 | 0 | 0 | 90
11 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Formal work order for Sinking of 4 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1,2,3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000811/2024-2025 | 3306/BD | 26/11/2024 | 24/02/2025 | UTPAL CONSTRUCTION & CO. | 103.47 | 21.84 | 21.11 | 100
12 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at OHR site within Dakshin Akhratala w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000147/2025-2026 | 996/HSD | 04/06/2025 | 14/06/2025 | M/S DATTA ENTERPRISE. | 0.95 | 0 | 0 | 100
13 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Acceptance cum work order for Digitalisation of pipeline alignment, elevation survey and asset evaluation of under Nazat, Dakshin Akhratala mouza under Dakshin Akhratala W/S Scheme, Sandeshkhali-I block under Hasnabad Sub-Division. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002369/2024-2025 | 578/HSD | 17/03/2025 | 27/03/2025 | MERCHANDISE-INDIA | 2.11 | 0 | 0 | 100
14 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Quotation for LT Service Connection at PH-II of Dakshin Akhratala W/S scheme under Sandeshkhali CCC |  |  | BILL/03274/2024-2025 | BP-285 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.97 | 0 | 0 | 0
15 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | New LT Service Connection at Pump House No-V under Dakshin Akhratala Water Supply Scheme under Sandeshkhali CCC |  |  | BILL/02083/2025-2026 |  | 24/09/2025 | 24/09/2025 | W.B.S.E.D.C.L (SANDESHKHALI CCC) | 3.92 | 0 | 0 | 0
16 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Quotation for LT Service Connection at PH-III of Dakshin Akhratala W/S scheme under Sandeshkhali CCC |  |  | BILL/03275/2024-2025 | BP-284 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0 | 0
17 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Quotation for LT Service Connection at PH-IV of Dakshin Akhratala W/S scheme under Sandeshkhali CCC |  |  | BILL/03276/2024-2025 | BP-283 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.7 | 0 | 0 | 0
18 | NORTH 24 PARGANAS | Sandeshkhali-I | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | "Battala BDO Office to Nazat Puratan Hatkhola Road" and Basirhat Pifa-Raghabpur Murarisha kalinagar Road". |  |  | BILL/00240/2025-2026 |  | 16/05/2025 | 16/05/2025 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 87.87 | 0 | 0 | 0
19 | NORTH 24 PARGANAS | Sandeshkhali-I | Eastern Mechanical | Dakshin Akhratala Piped Water Supply Scheme | SM/18617 | New | Quotation for LT Service Connection at PH-I of Dakshin Akhratala W/S scheme under Sandeshkhali CCC. |  |  | BILL/03277/2024-2025 | BP-286 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.83 | 0 | 0 | 0
Total | [13 empty] | 1424.72 | 418.52 | 29.38