## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC | SM/18618 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Banglani Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000717/2023-2024 | 2518/BD | 22/08/2023 | 20/11/2023 | KINGS & CO. | 606.14 | 58.67 | 9.68 | 59
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC | SM/18618 | Augmentation | Additional Survey work for DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002498/2021-2022 | 457 / BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.07 | 1.07 | 100 | 100
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC | SM/18618 | Augmentation | Route Survey, Design Drawing & DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/003053/2021-2022 | 456/BHT | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC | SM/18618 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1238/BD | 25/04/2023 |  | Resource Division | 146.14 | 0 | 0 | 0
Total | [13 empty] | 758.29 | 64.68 | 8.53