## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 3091/BD | 10/10/2023 | 10/10/2023 | Resource Division | 11.72 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 4369/BD | 10/11/2023 | 10/11/2023 | Resource Division | 1.35 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | Augmentation | Preparation of DPR in connection of augumentation of Sohai Swetpur Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000678/2022-2023 | 455/BSD | 20/05/2022 | 19/06/2022 | RADIANT | 3.38 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | Assistant Engineer | Junior Engineer | ORD/001842/2023-2024 | 1117./1/BSD | 09/02/2024 | 13/02/2024 | BIBHAS PAL. | 0.88 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | Augmentation | Formal work order for construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Swetpur (Zone-II) water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2023-2024 | 2594/BD | 28/08/2023 | 28/08/2025 | SINGHA ROY & CO. | 523.5 | 0 | 0 | 8
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. | SM/18712 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Swetpur-II Water Supply Scheme under JJM programme in Deganga block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001017/2024-2025 | 524/BD | 17/02/2025 | 18/05/2025 | A.P POWER & CONCRETE | 192.44 | 0 | 0 | 0
Total | [13 empty] | 22073.05 | 0 | 0