## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 2181/BD | 02/08/2024 | 02/08/2024 | Resource Division | 13.02 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 2181/BD | 02/08/2024 | 02/08/2024 | Resource Division | 17.29 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | Augmentation | Acceptance cum Work Order for Restoration of bituminious road from Nagdaha Adibansipara more to Shibtala in Majhipara Palashi G.P within Barrackpore -I Block for repairing of damage of bituminous road in connection with Mathurabil water supply project (Zone I,II,III) of J.J.M. under Barrackpore-I Sub-Division of Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002486/2024-2025 | 95/BKP | 24/03/2025 | 08/04/2025 | CHOWDHURY CONSTRUCTION. | 2.26 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | Augmentation | Acceptance cum Work Order for Restoration of bituminious road from Shibtala to Tarikhana more in Majhipara Palashi G.P. within Barrackpore-1 Dev. Block for repairing of damages in bituminous roads in connection with Mathurabil water supply project (Zone-I,II,III) of J.J.M. under Barrackpore Sub-Division of Barasat Division , P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002487/2024-2025 | 96/BKP | 24/03/2025 | 08/04/2025 | M/S RANA ENTERPRISE. | 4.41 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | Augmentation | Restoration charges for road damages for cutting between Ghoshpara Jaguli Road. |  |  | BILL/01623/2024-2025 | BP-2024-25-479 | 28/01/2025 | 28/01/2025 | EXECUTIVE ENGINEER, P.W.D., BARRACKPORE DIVN | 63.83 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | Augmentation | Formal work order for Name of Work: Laying Distribution System including construction of Surface drain, Land development and allied works at Zonal Head work with repair & renovation of 450 cum & 700 cum capacity OHR, Chlorine & Guard Room, Boundary wall at Head Works of Zone-I & II respectively with construction (Zone-III) of 500 cum capacity OHR, Chlorine & Guard Room and Boundary wall for Augmentation of Mathurabil surface based Water supply scheme at Zone-I,II & III of JJM within Barrackpore-I Block in the district North 24Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001696/2023-2024 | 353/BD | 02/02/2024 | 01/02/2027 | UMWELT ENGINEER PVT.LTD. | 2105.41 | 0 | 0 | 90
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. | SM/19110 | Augmentation | Formal work order for Construction of Ground Level Clear Water Reservoir (Capacity 250 Cum) and High Lift Pump House including allied works in Connection to augmentation of Mathurabill surface based water supply scheme at Zone- I, II & III within Barrackpore Block in the district of North 24 Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 2099/BD | 26/07/2024 | 01/04/2026 | M/S B.K.ENTERPRISE. | 235.53 | 0 | 0 | 100
Total | [13 empty] | 2441.76 | 0 | 0