## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Annual Maintenance Contract (AMC) for Computers Printers UPS and other related peripherals installed in various water testing laboratories under office of the Executive Engineer, Barasat Division P.H.E.Dte. (for the period 01.10.2023 to 30.09.2024). | Assistant Engineer |  | ORD/001387/2023-2024 | 871/BST | 29/09/2023 | 29/09/2024 | CSS INFOSOLUTION. | 2.41 | 1.41 | 58.55 | 85
2 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Acceptance cum work order for Engagement of Laboratory personnel at 9(Nine) nos. Sub-District Water Testing Laboratory . (Bodai SDL, Bishnupur SDL, Bagda SDL, Chandpara SDL, Habra SDL, Basirhat SDL ,Gokna SDL, Haroa SDL & Hingalganj SDL) and North 24 Parganas District Water Laboratory for 12 (Twelve) months w.e.f 01.01.2024 to 31.12.2024. | Assistant Engineer |  | ORD/001625/2023-2024 | 4879/BD | 29/12/2023 | 29/12/2024 | M/S B.K.ENTERPRISE. | 95.2 | 46.34 | 48.68 | 81
3 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Annual Maintenance Contract (AMC) for Computers Printers UPS and other related peripherals installed in various water testing laboratories under office of the Executive Engineer, Barasat Division P.H.E.Dte. (for the period 01.10.2024 to 31.12.2024) |  | Junior Engineer | ORD/000902/2024-2025 | 1120/BST | 30/09/2024 | 31/12/2024 | CSS INFOSOLUTION. | 0.6 | 0.6 | 100 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Annual Maintenance Contract (AMC) for Computers Printers UPS and other related peripherals installed in various water testing laboratories under office of the Executive Engineer, Barasat Division P.H.E.Dte. (for the period 01.01.2025 to 31.03.2025) |  | Junior Engineer | ORD/001506/2024-2025 | 1467/BST | 31/12/2024 | 31/03/2025 | CSS INFOSOLUTION. | 0.6 | 0.6 | 100 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Acceptance cum work order for Engagement of Laboratory personnel at 9(Nine) nos. Sub-District Water Testing Laboratory .(Bodai SDL, Bishnupur SDL, Bagda SDL, Chandpara SDL, Habra SDL, Basirhat SDL ,Gokna SDL, Haroa SDL & Hingalganj SDL) and North 24 Parganas District Water Laboratory for 12 (Twelve) months w.e.f 01.01.2025 to 31.12.2025. | Assistant Engineer |  | ORD/001107/2024-2025 | 3809/BD | 31/12/2024 | 31/12/2025 | M/S B.K.ENTERPRISE. | 96.97 | 51.55 | 53.16 | 6
6 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01171/2024-2025 | BP-2024-25-351 | 01/10/2024 | 01/10/2024 | FOSET BARRACKPORE SUB-CENTRE. | 0.63 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01452/2024-2025 | BP-2024-25-465 | 10/12/2024 | 10/12/2024 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01365/2024-2025 | BP-2024-25-455 | 20/11/2024 | 20/11/2024 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01456/2024-2025 | BP-2024-25-466 | 10/12/2024 | 10/12/2024 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01369/2024-2025 | BP-2024-25-454 | 19/11/2024 | 19/11/2024 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01455/2024-2025 | BP-2024-25-462 | 10/12/2024 | 10/12/2024 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01170/2024-2025 | BP-2024-25-346 | 01/10/2024 | 01/10/2024 | PASCHIMBANGA VIGYAN MANCHA. | 0.69 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01370/2024-2025 | BP-2024-25-457 | 19/11/2024 | 19/11/2024 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01366/2024-2025 | BP-2024-25-452 | 19/11/2024 | 19/11/2024 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01169/2024-2025 | BP-2024-25-359 | 01/10/2024 | 01/10/2024 | BITHARI DISHA. | 0.69 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01367/2024-2025 | BP-2024-25-453 | 19/11/2024 | 19/11/2024 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01457/2024-2025 | BP-2024-25-462 | 10/12/2024 | 10/12/2024 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01453/2024-2025 | BP-2024-25-467 | 10/12/2024 | 10/12/2024 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01368/2024-2025 | BP-2024-25-456 | 19/11/2024 | 19/11/2024 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01454/2024-2025 | BP-2024-25-464 | 10/12/2024 | 10/12/2024 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01168/2024-2025 | BP-2024-25-347 | 01/10/2024 | 01/10/2024 | PATHER PANCHALI SEVA SAMITY. | 0.69 | 0 | 0 | 0
22 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01166/2024-2025 | BP-2024-25-351 | 01/10/2024 | 01/10/2024 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.69 | 0 | 0 | 0
23 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01167/2024-2025 | BP-2024-25-348 | 01/10/2024 | 01/10/2024 | YOUTH DEVELOPMENT CENTER | 0.69 | 0 | 0 | 0
24 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01703/2024-2025 | BP-2024-25-658 | 29/03/2025 | 29/03/2025 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
25 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01627/2024-2025 | BP-2024-25-484 | 28/01/2025 | 28/01/2025 | BITHARI DISHA. | 0.5 | 0 | 0 | 0
26 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01626/2024-2025 | BP-2024-25-485 | 28/01/2025 | 28/01/2025 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
27 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00854/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
28 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/02079/2024-2025 | W/113 | 04/07/2025 | 04/07/2025 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
29 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00843/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
30 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01701/2024-2025 | BP-2024-25-659 | 29/03/2025 | 29/03/2025 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
31 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00379/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
32 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01657/2024-2025 | BP-2024-25-489 | 11/02/2025 | 11/02/2025 | PASCHIMBANGA VIGYAN MANCHA. | 0.5 | 0 | 0 | 0
33 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00097/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
34 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00853/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
35 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00842/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
36 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00846/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00849/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
38 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/02081/2024-2025 | W/113 | 04/07/2025 | 04/07/2025 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
39 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01658/2024-2025 | BP-2024-25-490 | 11/02/2025 | 11/02/2025 | FOSET BARRACKPORE SUB-CENTRE. | 0.5 | 0 | 0 | 0
40 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01659/2024-2025 | BP-2024-25-491 | 11/02/2025 | 11/02/2025 | YOUTH DEVELOPMENT CENTER | 0.49 | 0 | 0 | 0
41 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01700/2024-2025 | BP-2024-25-659 | 29/03/2025 | 29/03/2025 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
42 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01702/2024-2025 | BP-2024-25-659 | 29/03/2025 | 29/03/2025 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
43 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00845/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
44 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00092/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
45 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00378/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
46 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00095/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
47 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00094/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
48 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/02077/2024-2025 | W/113 | 04/07/2025 | 04/07/2025 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
49 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/02080/2024-2025 | W/113 | 04/07/2025 | 04/07/2025 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
50 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01704/2024-2025 | BP-2024-25-654 | 29/03/2025 | 29/03/2025 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
51 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/02078/2024-2025 | W/113 | 04/07/2025 | 04/07/2025 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
52 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00851/2025-2026 | W/179 | 12/08/2025 | 12/08/2025 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
53 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00096/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
54 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01705/2024-2025 | BP-2024-25-657 | 29/03/2025 | 29/03/2025 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
55 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/01628/2024-2025 | BP-2024-25-483 | 28/01/2025 | 28/01/2025 | PATHER PANCHALI SEVA SAMITY. | 0.49 | 0 | 0 | 0
56 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00376/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
57 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00093/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
58 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Certify that the work has been done as per specification, terms & condition. |  |  | BILL/02076/2024-2025 | W/113 | 04/07/2025 | 04/07/2025 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. | SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. |  |  | BILL/00377/2025-2026 | W/113 | 04/07/2025 | 04/07/2025 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
Total | [13 empty] | 224.4 | 100.51 | 44.79