## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Procurement of Chemical & Consumables, Glassware etc. for smooth running of Mangal Pandey WTP Water Testing Laboratory under North 24 Parganas W/S Division-I, PHE Dte., Govt. of W.B. | SM/06633 | Support-WQMSP | Supply and delivery of Chemicals & Consumables Glassware etc. for the smooth running of the laboratory for 1 year for Block level sample, Private Sample & Referral sample testing monitoring under the Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000060/2020-2021 | 63/NWSD-I | 19/01/2021 | 20/01/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 5.74 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Procurement of Chemical & Consumables, Glassware etc. for smooth running of Mangal Pandey WTP Water Testing Laboratory under North 24 Parganas W/S Division-I, PHE Dte., Govt. of W.B. | SM/06633 | Support-WQMSP | Engagement of resource person for supervising the protocol/ standard operating procedure/ technical documentation of Water Testing Laboratory Quality management system as per ISO/IEC 17025:2017 including supply of required Reagents, Standard Reference material & solutions traceable to NIST, Chemicals & Consumables, Glassware,Calibration of instruments etc. to comply with NABL accreditation system of Mangal Pandey WTP Water testing laboratory. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000070/2020-2021 | 1001/NWSD-I | 08/12/2020 | 08/06/2021 | LAB ANALYTICS | 4.56 | 0 | 0 | 0
Total | [13 empty] | 10.3 | 0 | 0