## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) | SM/07605 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-I). | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000041/2020-2021 | 74/NWSD-I | 20/01/2021 | 20/04/2021 | A.K.C. SUPPLY & CONSTRUCTION | 71.32 | 112.91 | 158.3 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) | SM/07605 | Retrofitting | Continuation order for the work of Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.12.2023 to 31.05.2024.(183 days)].(Car No.WB25J7778.) | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000214/2023-2024 | 1920/NWSD-I | 29/11/2023 | 30/05/2024 | GITA DAS | 0.87 | 0.74 | 84.7 | 16
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) | SM/07605 | Retrofitting | Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2023 to 30.11.2023.(183 days)].(Car No.WB25J7778.) | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000044/2023-2024 | 632/NWSD-I | 25/05/2023 | 24/11/2023 | GITA DAS | 0.87 | 1.15 | 132.58 | 20
Total | [13 empty] | 73.06 | 114.8 | 157.12