## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07607 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000052/2020-2021 | 104/NWSD-I | 01/02/2021 | 17/04/2021 | SUDHAMAY MAJUMDAR | 63.29 | 106.65 | 168.52 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) | SM/07607 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas W/S Division-I, P.H.E. Dte. for 184 (one hundred eighty four) days w.e.f 01/03/2023 to 31/08/2023.[Car No.WB 25L 4241]. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000200/2022-2023 | 168/NWSD-I | 16/02/2023 | 19/08/2023 | M/S. SHUBHA ENTERPRISE | 0.87 | 1.06 | 120.92 | 65
Total | [13 empty] | 64.16 | 107.71 | 167.87