## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) | SM/08039 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block under North 24 Pgs. Water Supply Division-I, PHE Dte. ( Phase-II). | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000009/2021-2022 | 385/NWSD-I | 12/05/2021 | 10/08/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 237.57 | 427.71 | 180.04 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) | SM/08039 | Retrofitting | Continuation order for the work of Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition on daily rental basis for JJM works under Office of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) w.e.f. 01.07.2024 to 31.12.2024. [Vehicle No.WB 23C 5335] | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000058/2024-2025 | 963/NWSD-I | 26/06/2024 | 27/12/2024 | M/S. SHUBHA ENTERPRISE | 0.86 | 2.31 | 267.03 | 100
Total | [13 empty] | 238.43 | 430.02 | 180.36