## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under (Phase-I) for Arsenic affected areas of North 2 | SM/08046 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under Phase-I for Arsenic affected areas of North 24 Parganas Water Supply Division - I, P.H.E. Dte. of Barasat-I Block at Mouza Kharki, J.L. No.132, Naksa, J.L. No.131 and Kotra, J.L.No.133 under Kotra Gram Panchayat. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000010/2021-2022 | 413/NWSD-I | 27/05/2021 | 25/08/2021 | H. I. ENTERPRISE | 91.88 | 0 | 0 | 1
Total | [13 empty] | 91.88 | 0 | 0