## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). | SM/08234 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PARMADAN Water Supply Scheme at BAGDAH Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-I) | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000068/2021-2022 | 865/NWSD-I | 08/10/2021 | 07/12/2021 | M/S - SUKANTA ENTERPRISE | 49.19 | 50.37 | 102.4 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). | SM/08234 | Retrofitting | Continuation order for the work of Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) days w.e.f. 01.07.2023 to 31.12.2023. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000054/2023-2024 | 787/NWSD-I | 23/06/2023 | 24/12/2023 | BADAL GHOSH | 0.86 | 1.67 | 192.54 | 20
Total | [13 empty] | 50.05 | 52.03 | 103.96