## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Santoshpur Zone-II Water SupplyScheme at Bongaon Block (Phase-II). | SM/08238 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II). | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000063/2021-2022 | 848/NWSD-I | 07/10/2021 | 06/12/2021 | M/S. R. M. CONSTRUCTION | 62.2 | 61.73 | 99.24 | 1
Total | [13 empty] | 62.2 | 61.73 | 99.24