## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). | SM/08239 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II) | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000064/2021-2022 | 863/NWSD-I | 08/10/2021 | 22/12/2021 | M/S. TARAK CHANDRA PAUL | 80.93 | 34.91 | 43.14 | 1
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). | SM/08239 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas W/S Division-I, P.H.E. Dte. for 181 (one hundred eighty one) days w.e.f 01/09/2022 to 28/02/2023. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000122/2022-2023 | 1018/NWSD-I | 24/08/2022 | 21/02/2023 | M/S. SHUBHA ENTERPRISE | 0.86 | 1.81 | 210.52 | 100
3 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). | SM/08239 | Retrofitting | Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2023 to 30.11.2023.(183 days)].(Car No.WB25J7778.) | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000044/2023-2024 | 632/NWSD-I | 25/05/2023 | 24/11/2023 | GITA DAS | 0.87 | 0.2 | 22.93 | 20
4 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). | SM/08239 | Retrofitting | Continuation order for the work of Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) days w.e.f. 01.07.2023 to 31.12.2023. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000054/2023-2024 | 787/NWSD-I | 23/06/2023 | 24/12/2023 | BADAL GHOSH | 0.86 | 0.43 | 50.28 | 20
Total | [13 empty] | 83.52 | 37.36 | 44.73