## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within command area of Surface water based Water Supply Scheme (Zone-VI) at BERABERIA OHR site from Arsenic affected areas of North 24 Parganas water supply Division - I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000084/2021-2022 | 1005/NWSD-I | 24/11/2021 | 22/02/2022 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 224.61 | 202.33 | 90.08 | 100
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 03/NWSD-I | 03/01/2022 | 03/01/2022 | Resource Division | 11 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | Retrofitting | Hiring of Diesel Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 182 (One Hundrad Eighty Two) Days. w.e.f. 01.01.2024 to 30.06.2024. | ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000327/2023-2024 | 2196/NWSD-I | 29/12/2023 | 28/06/2024 | BADAL GHOSH | 0.86 | 2.25 | 259.96 | 16
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | Retrofitting | Continuation order for the work of Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2024 to 19.06.2024.(19 days)].(Car No.WB25J7778.) | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000013/2024-2025 | 816/NWSD-I | 29/05/2024 | 17/06/2024 | GITA DAS | 0.09 | 0.2 | 225.61 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | Retrofitting | Continuation order for the work of Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) w.e.f. 01.07.2024 to 31.12.2024. [Vehicle No.WB 25L4241]. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000016/2024-2025 | 932/NWSD-I | 21/06/2024 | 22/12/2024 | M/S. SHUBHA ENTERPRISE | 0.87 | 1.87 | 213.43 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block | SM/08241 | Retrofitting | Continuation order for the work of Hiring of Diesel Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) Days. w.e.f. 01.07.2024 to 31.12.2024. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000015/2024-2025 | 948/NWSD-I | 24/06/2024 | 25/12/2024 | BADAL GHOSH | 0.87 | 2.22 | 253.8 | 0
Total | [13 empty] | 238.31 | 208.86 | 87.64