## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block | SM/08243 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within command area of surface water based water supply scheme ( Zone III) at Algoria OHR site at Barasat-I Block for Arsenic affected areas of North 24 Parganas water supply Division - I, PHE Dte. (2nd Call) | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000102/2021-2022 | 1130/NWSD-I | 22/12/2021 | 20/02/2022 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 84.33 | 0 | 0 | 100
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block | SM/08243 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 02/NWSD-I | 03/01/2022 | 03/01/2022 | Resource Division | 8.77 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block | SM/08243 | Retrofitting | Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 182 (One Hundred Eighty Two) w.e.f. 01.01.2024 to 30.06.2024. [Vehicle No.WB 25L4241] | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000265/2023-2024 | 2201/NWSD-I | 29/12/2023 | 28/06/2024 | M/S. SHUBHA ENTERPRISE | 0.86 | 0 | 0 | 0
Total | [13 empty] | 93.96 | 0 | 0