## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block | SM/08244 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of surface water based water supply scheme (Zone VII) at Khoru OHR site at Amdanga Block for Arsenic affected areas of North 24 Parganas water supply Division - I, PHE Dte. (2nd. Call) | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000070/2021-2022 | 1129/NWSD-I | 22/12/2021 | 20/02/2022 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 78.07 | 57.77 | 74 | 100
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block | SM/08244 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 01/NWSD-I | 03/01/2022 | 03/01/2022 | Resource Division | 7.98 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block | SM/08244 | Retrofitting | Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition on daily rental basis for JJM works under Office of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 182 (One Hundred Eighty Two) w.e.f. 01.01.2024 to 30.06.2024. [Vehicle No.WB 23C 5335] | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000266/2023-2024 | 2200/NWSD-I | 29/12/2023 | 28/06/2024 | M/S. SHUBHA ENTERPRISE | 0.86 | 2.24 | 262.04 | 100
Total | [13 empty] | 86.91 | 60.01 | 69.06