## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mollahati Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (Phase-I). | SM/08731 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MOLLAHATI Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000074/2021-2022 | 962/NWSD-I | 16/11/2021 | 30/01/2022 | ONKAR ENTERPRISE | 92.39 | 93.37 | 101.05 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mollahati Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (Phase-I). | SM/08731 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed it on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas W/S Sub-Division-I, P.H.E. Dte. for 6(Six) months, i.e. 181 days. [w.e.f. 01.11.2024 to 30.04.2025] (Car No.WB25K0619) | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000064/2024-2025 | 1571/NWSD-I | 25/10/2024 | 24/04/2025 | M/S. SHUBHA ENTERPRISE | 0.86 | 0.66 | 76.45 | 0
Total | [13 empty] | 93.25 | 94.02 | 100.83