## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Patulia Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (HQ-II) |  | ORD/000121/2021-2022 | 1194/NWSD-I | 31/12/2021 | 15/01/2022 | UMWELT ENGINEER PRIVATE LIMITED | 4.88 | 4.88 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works within command area of Patulia Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000038/2022-2023 | 670/ NWSD-I | 26/05/2022 | 31/10/2026 | CONCORD ENGINEERING | 786.84 | 613.09 | 77.92 | 90
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 675/NWSD-I | 26/05/2022 | 26/05/2022 | Resource Division | 69.9 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 642/NWSD-I | 20/05/2022 | 20/05/2022 | Resource Division | 58.46 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Repair and renovation works for 900 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir, Boundary wall, Pump House and construction of Godown at H/W site with other allied works at Patulia W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000113/2023-2024 | 1264/NWSD-I | 21/08/2023 | 20/10/2023 | M/S. ASOKE GHOSH AND BROTHERS | 55.54 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | CONSTRUCTION OF PUMP HOUSE (4.88M X 3.66M) INCLUDING SANITARY ARRANGEMENT at Ruiya Verir Gate Bazar, Dag no.- 220, Khatian no.- 715, J.L. no- 20 under Patulia Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. (Sl. No. 07). | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000147/2023-2024 | 1510/NWSD-I | 22/09/2023 | 21/11/2023 | M/S. ASOKE GHOSH AND BROTHERS | 5.57 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | CONSTRUCTION OF PUMP HOUSE (4.88M X 3.66M) INCLUDING SANITARY ARRANGEMENT at Patulia Girls School Ground ( Bandipur Play Ground ) Dag No. 1552, LR KH No.282 , JL No. 04 under Patulia Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. (Sl. No. 08) | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000148/2023-2024 | 1434/NWSD-I | 11/09/2023 | 10/11/2023 | A. S. ENTERPRISE | 5.57 | 5.54 | 99.39 | 100
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1842/NWSD-I | 10/11/2023 | 10/11/2023 | Resource Division | 3.08 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000275/2023-2024 | 70/NWSD-I | 10/01/2024 | 09/02/2024 | BIBHAS PAL | 4.94 | 0.53 | 10.64 | 100
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10100 | Augmentation | Road restoration regarding PMGSY road Bandipur Sashthitala to Iswaripur more , Package No. WB 01 396 (Iswaripur more towards Patulia /Bandipur tank Barobagan more near shib mandir to duisatin pukur under Patulia scheme under Barrackpore -II Block. |  |  | BILL/00317/2024-2025 | 335/PFMS/24-25 | 21/01/2025 | 21/01/2025 | EXECUTIVE ENGINEER, WBSRDA, NORTH 24 PARGANAS DIVISION | 21.16 | 0 | 0 | 0
Total | [13 empty] | 1015.95 | 624.03 | 61.42