## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Ichhlampur (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000140/2021-2022 | 1187/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.8 | 3.8 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Ichhlampur Zone-II Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/000018/2022-2023 | 526/NWSD-I | 25/04/2022 | 24/07/2022 | H. I. ENTERPRISE | 335.97 | 72.07 | 21.45 | 85
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 608/NWSD-I | 17/05/2022 | 17/05/2022 | Resource Division | 11.15 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 650/NWSD-I | 23/05/2022 | 23/05/2022 | Resource Division | 24.21 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Renovation of AIRP at Ichhlampur Zone-II Water Supply Scheme of capacity 66.75 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000056/2024-2025 | 1587/NWSD-I | 29/10/2024 | 27/04/2025 | GHOSH CONSTRUCTION | 54.12 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir OF 350 CUM, Pump House at Head Works Site, Special Repair & Renovation of Boundary Wall at Head Work Site & other allied works at Ichhlampur Zone-II W/S Scheme Under Bongaon Block In The District Of North 24 Pargana(S) Under N 24 Pgs W/S Div-I, Phe Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000135/2023-2024 | 1394/NWSD-I | 05/09/2023 | 04/11/2023 | SAHA CONSTRUCTION & CO. | 31.49 | 0 | 0 | 12
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 1309/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 1.23 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Continuation order for the work of Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 181 (One Hundred Eighty One) w.e.f. 01.01.2025 to 30.06.2025. [Vehicle No.WB 25L4241]. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000235/2024-2025 | 1976/NWSD-I | 31/12/2024 | 30/06/2025 | M/S. SHUBHA ENTERPRISE | 0.86 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. | SM/10101 | Augmentation | Additional laying of UPVC pipe and allied work under Augmentation work at Ichhlampur (Zone - II) W/S Scheme, Bongaon Block of North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000028/2025-2026 | 799/NWSD-I | 28/05/2025 | 24/12/2025 | OM CONSTRUCTION | 16.95 | 0 | 0 | 67
Total | [13 empty] | 484.37 | 75.87 | 15.66