## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Bagangram Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000196/2021-2022 | 236/NWSD - I | 24/02/2022 | 03/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.52 | 4.52 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Bangangram Zone-II Water Supply Scheme district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000033/2022-2023 | 631/NWSD-I | 19/05/2022 | 17/08/2022 | S & P ENTERPRISE | 434.49 | 209.19 | 48.15 | 36
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Special Repair and renovation of Pump House & Allied Works for Head Works site & 2nd Tube Well site at Bagangram Zone-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000023/2023-2024 | 379/NWSD-I. | 05/04/2023 | 20/05/2023 | GHOSH CONSTRUCTION | 5.25 | 0 | 0 | 28
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Special Repair and Renovation of Pump House & Allied Works for Head Works site & 2nd Tube Well Site at BAGANGRAM ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000005/2023-2024 | 379/NWSD-I | 05/04/2023 | 20/05/2023 | GHOSH CONSTRUCTION | 5.25 | 4.01 | 76.48 | 28
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 612/NWSD-I | 17/05/2022 | 17/05/2022 | Resource Division | 14.93 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 649/NWSD-I | 23/05/2022 | 23/05/2022 | Resource Division | 16.66 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Repair and renovation works for 350 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir , Boundary wall at H/W site and PH-II with other allied works at Bagangram (Z-II) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000109/2023-2024 | 1262/NWSD-I | 21/08/2023 | 20/10/2023 | GHOSH CONSTRUCTION | 32.24 | 31.81 | 98.67 | 100
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0.18 | 3.33 | 100
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas | SM/10102 | Augmentation | Laying of pipe line & special measure for protection of road and other allied works at different location under Augmentation work at Bagangram Zone-II W/S. Scheme in Bongaon Block under North 24 Parganas W/S. Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000006/2025-2026 | 695/NWSD-I | 14/05/2025 | 29/05/2025 | GHOSH CONSTRUCTION | 11.37 | 0 | 0 | 0
Total | [13 empty] | 529.98 | 249.71 | 47.12