## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Paschim Panchberia (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000124/2021-2022 | 1193/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.96 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 165 m Length in Head work site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000148/2022-2023 | 275/NWSD-I | 14/03/2023 | 28/04/2023 | NIKHIL SAMADDAR | 19.75 | 0 | 0 | 100
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Service Road (60 Mtr. Length X 3 Mtr. Width) at Headwork site & Service Road (25 Mtr. Length X 2 Mtr. Width) at pump house site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000150/2022-2023 | 278/NWSD-I | 14/03/2023 | 28/04/2023 | RAJ ENTERPRISE | 6.19 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 40 m Length in 2nd Pump house site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000151/2022-2023 | 276/NWSD-I | 14/03/2023 | 28/04/2023 | ASHIM ENTERPRISE | 5.18 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Special Repair & Renovation of .Pump house and Allied Works at Head Works Site & 2nd Pump house site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000149/2022-2023 | 277/NWSD-I | 14/03/2023 | 28/04/2023 | GHOSH CONSTRUCTION | 5.2 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of Paschim Panchberia Zone-II Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/000032/2022-2023 | 617/NWSD-I | 17/05/2022 | 15/08/2022 | UMWELT ENGINEER PRIVATE LIMITED | 326.94 | 0 | 0 | 85
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 613/NWSD-I | 17/05/2022 | 17/05/2022 | Resource Division | 3.8 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 651/NWSD-I | 23/05/2022 | 23/05/2022 | Resource Division | 7.22 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Renovation of AIRP at Paschim Pachneria Zone-II Water Supply Scheme of capacity 59.88 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000100/2024-2025 | 1739/NWSD-I | 28/11/2024 | 27/05/2025 | MONDAL PRECISION PRIVATE LIMITED | 68.4 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10104 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum at Paschim Panchberia Zone-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000089/2023-2024 | 1099/NWSD-I | 01/08/2023 | 15/09/2023 | MONDAL CONSTRUCTION | 13.79 | 0 | 0 | 100
Total | [13 empty] | 460.43 | 0 | 0