## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Bilkanda (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (HQ-II) |  | ORD/000135/2021-2022 | 1183/NWSD-I | 31/12/2021 | 15/01/2022 | UMWELT ENGINEER PRIVATE LIMITED | 4.87 | 4.87 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works within command area of Bilkanda Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000036/2022-2023 | 706/ NWSD-I | 07/06/2022 | 05/09/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 679.28 | 676.84 | 99.64 | 100
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 739/NWSD-I | 13/06/2022 | 13/06/2022 | Resource Division | 13.93 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 750/NWSD-I | 14/06/2022 | 14/06/2022 | Resource Division | 52.13 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 641/NWSD-I | 20/05/2022 | 20/05/2022 | Resource Division | 52.13 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Repair and renovation works for 1000 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir, Boundary wall, Pump House at H/W site and PH-II with other allied works at Bilkanda (Z-I) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000141/2023-2024 | 1400/NWSD-I | 05/09/2023 | 04/11/2023 | SUDHAMAY MAJUMDAR | 47.57 | 47.11 | 99.02 | 100
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000275/2023-2024 | 70/NWSD-I | 10/01/2024 | 09/02/2024 | BIBHAS PAL | 4.94 | 1.09 | 21.96 | 100
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide Notification No. 03/2022 Central tax rate dt.13/07/2022 for the work of "Laying of distribution pipeline including providing FHTC at Bilkanda Zone-I W/S Scheme under NWSD-I, P.H.E. Dte. Tender No.28/eT/NWSD-I of 2022-23, Work Order No.706/NWSD-I dt.07/06/2022, Enhancement GST Sanction No. PHE/IV/3260/W-698/23 dt.19/10/2023. |  |  | BILL/00127/2024-2025 | 181/PFMS/24-25 | 03/09/2024 | 03/09/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 31.18 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Road restoration due to laying of pipeline of Augmention work at Bilkanda (Zone-I) W/S Scheme in Barrackpore-II Block under Northn24 Pgs W/S Div-I, P.H.E, Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2025-2026 | 849/NWSD-I | 03/06/2025 | 03/07/2025 | A. S. ENTERPRISE | 8.63 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Construction of Latrine at Pump House-II and Road Restoration due to laying of pipeline under Augmentation work at Bilkanda-I W/S Scheme in Barrackpore-II Block under North 24 Pgs W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000207/2024-2025 | 392/NWSD-I | 12/03/2025 | 11/04/2025 | B. S. ENTERPRISE | 11.73 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. | SM/10105 | Augmentation | Construction of Godown at Head Work site for Augmentation of Bilkanda (Zone-I) Water Supply Scheme in Bbarrackpore-II Block of North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000129/2024-2025 | 104/NWSD-I | 17/01/2025 | 01/02/2025 | M/S. PHOENIX INFRASTRUCTURE | 7.43 | 7.4 | 99.56 | 100
Total | [13 empty] | 918.44 | 737.31 | 80.28