## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Santoshpur (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000123/2021-2022 | 1196/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 4.62 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Santoshpur Zone-II Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000019/2022-2023 | 544/NWSD-I | 28/04/2022 | 27/07/2022 | PUSPA ENTERPRISE | 432.64 | 432.88 | 100.06 | 100
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 611/NWSD-I | 17/05/2022 | 17/05/2022 | Resource Division | 10 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 647/NWSD-I | 23/05/2022 | 23/05/2022 | Resource Division | 11.61 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Repair and renovation works for 350 cum. capacity R.C.C. Over Head water Reservoir and other allied works at Santoshpur (Zone-II) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000108/2023-2024 | 1261/NWSD-I | 21/08/2023 | 20/10/2023 | PUSPA ENTERPRISE | 51.13 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 1310/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 2.46 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Renovation of AIRP at Santoshpur-Zone-II Water Supply Scheme of capacity 82 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000061/2024-2025 | 1669/NWSD-I | 19/11/2024 | 14/11/2025 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 70.28 | 0 | 0 | 30
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10110 | Augmentation | Laying of distribution pipeline and allied work at Bongaon Block under Augmentation Scheme of Santoshpur W/S Scheme (Zone - II) within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000016/2025-2026 | 774/NWSD-I | 23/05/2025 | 19/12/2025 | M/S. S.S. ENTERPRISE | 19.51 | 0 | 0 | 0
Total | [13 empty] | 602.25 | 437.5 | 72.64