## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Santoshpur (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000122/2021-2022 | 1195/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.53 | 4.53 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000012/2023-2024 | 408/NWSD-I | 11/04/2023 | 26/05/2023 | RAKESH ENTERPRISE | 13.91 | 13.9 | 99.97 | 100
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 40 m Length in 2nd Pump house site at Santoshpur Zone - I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000016/2023-2024 | 410/NWSD-I | 11/04/2023 | 26/05/2023 | P & S ASSOCIATES | 5.17 | 4.33 | 83.63 | 100
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Special Repair & Renovation of Pump House at Head Works site & Service Road (60 Mtr. Length X 3 Mtr. Width) at Head Works site at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000015/2023-2024 | 411/NWSD-I | 11/04/2023 | 26/05/2023 | PRABIR KUMAR MONDAL | 7.22 | 6.8 | 94.24 | 45
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Special Repair & Renovation of Pump House at 2nd Pump house site & Service Road (25 Mtr. Length X 2 Mtr. Width) at 2nd Pump house site at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000017/2023-2024 | 412/NWSD-I | 11/04/2023 | 26/05/2023 | JEET ENTERPRISE | 4.18 | 3.65 | 87.18 | 35
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 146 m Length in Head work site at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000013/2023-2024 | 409/NWSD-I | 11/04/2023 | 26/05/2023 | AYUSH ENTERPRISE | 14.26 | 9.74 | 68.32 | 5
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 748/NWSD-I | 14/06/2022 | 14/06/2022 | Resource Division | 18.89 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 737/NWSD-I | 13/06/2022 | 13/06/2022 | Resource Division | 130.25 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of SANTOSHPUR Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/000039/2022-2023 | 704/NWSD-I | 07/06/2022 | 05/09/2022 | SUPRITI ENTERPRISE | 528.09 | 525.48 | 99.51 | 69
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 1311/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 5.54 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Renovation of AIRP at Santoshpur-Zone-I Water Supply Scheme of capacity 92 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000062/2024-2025 | 1670/NWSD-I | 19/11/2024 | 18/05/2025 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 80.35 | 0 | 0 | 35
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. | SM/10111 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
Total | [13 empty] | 816.98 | 568.43 | 69.58