## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with Providing functional household tap connection to every Household under Chandpur W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000115/2021-2022 | 1176/NWSD-I | 31/12/2021 | 07/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.99 | 3.99 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of Chandpur Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/000027/2022-2023 | 588/NWSD-I | 10/05/2022 | 08/08/2022 | H. I. ENTERPRISE | 227.12 | 204.13 | 89.87 | 87
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 648/NWSD-I | 23/05/2022 | 23/05/2022 | Resource Division | 2.16 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 609/NWSD-I | 17/05/2022 | 17/05/2022 | Resource Division | 9.02 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1837/NWSD-I | 10/11/2023 | 10/11/2023 | Resource Division | 3.08 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Repair And Renovation Works Of R.C.C. Elevated Reservoir Of 250 CUM, Pump House At Head Works Site, Special Repair & Renovation Of Boundary Wall At Head Work Site & Other Allied Works At Chandpur W/S Scheme Under Bagdag Block In The District Of North 24 Pargana(S) Under N 24 Pgs W/S Div-I, Phe Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000146/2023-2024 | 1433/NWSD-I | 11/09/2023 | 08/11/2024 | CHANDIMATA CONSTRUCTION | 26.87 | 5.85 | 21.78 | 5
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 1302/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 1.85 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Laying of pipeline & special measure for protection of road and other allied works at different location under Augmentation work at Chandpur W/S. Scheme in Bagda Block under North 24 Parganas W/S. Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000070/2024-2025 | 169/NWSD-I | 30/01/2025 | 01/03/2025 | A.K.C. SUPPLY & CONSTRUCTION | 24.42 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. | SM/10299 | Augmentation | CONSTRUCTION OF SERVICE ROAD OF 150 M LENGTH WITH PROTECTION WORK WITHIN THE COMMAND AREA UNDER CHANDPUR W/S SCHEME UNDER BAGDAH BLOCK OF NORTH 24 PARGANA(S) DISTRICT UNDER N 24 PGS W/S DIV-I, PHE DTE. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000343/2023-2024 | 444/NWSD-I | 11/03/2024 | 10/05/2024 | PATHIK PABAN NANDI | 29.73 | 0 | 0 | 100
Total | [13 empty] | 332.83 | 213.97 | 64.29