## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Bayra W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001905/2022-2023 | 6150 / EMD | 14/08/2022 | 13/09/2022 | TAMAL ENTERPRISE | 13.22 | 10.93 | 82.7 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under Bayra W/S Scheme District of 24 Pgs. (N), |  |  | ORD/001912/2022-2023 | 6149/-EMD | 14/08/2022 | 13/09/2022 | DEY ENTERPRISE | 13.22 | 10.93 | 82.7 | 1
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Bayra Water Supply Scheme in Bagdah Block under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/000048/2022-2023 | 867/NWSD-I | 21/07/2022 | 19/10/2022 | H. I. ENTERPRISE | 306.66 | 313.23 | 102.14 | 98
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 877/NWSD-I | 22/07/2022 | 22/07/2022 | Resource Division | 26.15 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr. Deep tube well by D.R. Rig method at Head Work Site at Boyra Water Supply Scheme under Bagdah Block within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000249/2023-2024 | 2028/NWSD-I | 13/12/2023 | 12/01/2024 | ACME CONSTRUCTION | 19.35 | 15.97 | 82.54 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials, Construction Boundary Wall & Service Road at Pump House and head work site, Augmentation of Bayra Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000057/2023-2024 | 640/NWSD-I | 26/05/2023 | 01/10/2026 | M/S. BUILDWELL | 156.3 | 24.81 | 15.87 | 35
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Inter connection with new Tube well at H/W site under Augmentation Scheme of Bayra within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000068/2024-2025 | 52/NWSD-I | 09/01/2025 | 16/01/2025 | ARUP CONSTRUCTION | 0.93 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Repairing and renovation of boundary illumination arrangement and allied works at P.H. No. I (OHR site) under Bayra W/S Scheme under EMSD-I, P.H.E.Dte. Dist.- 24PGS(N). | Assistant Engineer | Junior Engineer | ORD/000016/2025-2026 | 453/EMSD-I | 08/04/2025 | 08/05/2025 | ANJAN ENTERPRISE | 2.52 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Bayra Water Supply Scheme in Bagdah Block under district North 24 Parganas Water Supply Division-I, PHE. Dte. |  |  | BILL/00026/2025-2026 |  | 25/04/2025 | 25/04/2025 | H. I. ENTERPRISE | 16.7 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. | SM/10415 | Augmentation | Quotation for 10 KWp Solar power plant at P.H.No- I of Bayra ground water based water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/02085/2025-2026 |  | 24/09/2025 | 24/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.15 | 0 | 0 | 0
Total | [13 empty] | 555.18 | 375.87 | 67.7