## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | Augmentation | Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household under Paikpara Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000111/2021-2022 | 1172/NWSD-I | 31/12/2021 | 07/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.67 | 3.67 | 100 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I(Z-II) under Paikpara W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 14) |  |  | ORD/000124/2022-2023 | 6151/EMD | 11/11/2022 | 11/12/2022 | M/S DAS ENTERPRISE | 13.21 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 1212/NWSD-I | 13/10/2022 | 13/10/2022 | Resource Division | 22.89 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 457/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 58.1 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0.18 | 3.33 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 1303/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 22.89 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10546 | Augmentation | Laying of Distribution System including specials & valves, pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, construction works of R.C.C. Elevated Reservoir 400 m3, construction of Pump House, Boundary Wall in Headwork Site, Construction of Service Road (60 Mtr. Length X 3 Mtr.Width) at Headwork site of Paikpara Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000177/2023-2024 | 1681/NWSD-I | 30/10/2023 | 29/10/2024 | PATHIK PABAN NANDI | 542.96 | 74.82 | 13.78 | 35
Total | [13 empty] | 669 | 78.67 | 11.76