## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Mohonpur Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (HQ-II) |  | ORD/000128/2021-2022 | 1190/NWSD-I | 31/12/2021 | 15/01/2022 | UMWELT ENGINEER PRIVATE LIMITED | 4.88 | 4.88 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. Depth at 2nd Tube Well site within command area of Mohanpur Water Supply Scheme at Barrackpore-II Block under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) |  | ORD/000101/2022-2023 | 1409/NWSD-I | 13/12/2022 | 02/01/2023 | AUXILIARY TUBEWELL DRILLER | 21.05 | 15 | 71.25 | 1
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Construction of BOUNDARY WALL for 44 m Length, Special Repair & Renovation one Pump house and Allied Works & Service Road (25 Mtr. Length X 2 Mtr. Width) at 3rd. pump house site at Mohanpur Water Supply scheme in Barrackpur-II Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000019/2023-2024 | 447/NWSD-I | 25/04/2023 | 09/06/2023 | BANERJEE ENTERPRISE | 9.93 | 7.92 | 79.79 | 100
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 1839/NWSD-I | 10/11/2023 | 10/11/2023 | Resource Division | 15.4 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Construction of Boundary wall other allied works at proposed head work site at Babanpur (behind Santi Sarabar) of Mohanpur Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000137/2023-2024 | 1396/NWSD-I | 05/09/2023 | 04/11/2023 | DAS TRADING | 34 | 10.74 | 31.6 | 5
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Restoration & Development of road of proposed H/W Site at Babanpur (behind Santi Sarabar) & protection work of Boundary wall along pond sitde of existing Head Work site under Augmentation work at Mohanpur W/S Scheme within the jurisdiction of N24Pgs. W/S Sub-Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000040/2024-2025 | 1630/NWSD-I | 12/11/2024 | 12/12/2024 | A.K.C. SUPPLY & CONSTRUCTION | 26.81 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. Depth at Head Works site within command area of Mohanpur Water Supply Scheme at Barrackpore-II Block under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000036/2023-2024 | 653/NWSD-I | 29/05/2023 | 18/06/2023 | AUXILIARY TUBEWELL DRILLER | 21.07 | 17.12 | 81.26 | 100
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir of 250 Cum capacity at Head work site of Mohanpur water supply scheme and other ancilary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000138/2023-2024 | 1397/NWSD-I | 05/09/2023 | 04/11/2023 | DAS TRADING | 14.15 | 14.13 | 99.89 | 100
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Construction of Pump house (4.88m X 3.66m) including Sanitary arrenagement And strenthing the approach road along with other allied works at proposed head work site at Babanpur (behind Santi Sarabar) of Mohanpur Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000136/2023-2024 | 1395/NWSD-I | 05/09/2023 | 04/11/2023 | A.K.C. SUPPLY & CONSTRUCTION | 20.92 | 20.89 | 99.87 | 100
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000275/2023-2024 | 70/NWSD-I | 10/01/2024 | 09/02/2024 | BIBHAS PAL | 4.94 | 0.35 | 7.09 | 100
11 | NORTH 24 PARGANAS |  | Electrical | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MOHANPUR PIPED W/S SCHEME, T.W. No. IV, Block: Barrackpore-II, District - North 24 Pgs. under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1 | Junior Engineer3 | ORD/002510/2023-2024 | 426/ED | 29/02/2024 | 29/05/2024 | DEY ENTERPRISE | 10.43 | 10.16 | 97.45 | 100
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 670/NWSD-I | 18/04/2024 | 18/04/2024 | Resource Division | 74.34 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 214/NWSD-I | 02/02/2024 | 02/02/2024 | Resource Division | 12.32 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Electrical | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Quotation for New service connection at Mohanpur PWSS Head Works Site SM/10579 |  |  | BILL/06220/2023-2024 | 822 | 01/03/2024 | 01/03/2024 | WBSEDCL | 5.43 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. | SM/10579 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system, Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including 550 mm dia. pile foundation and pipe connection and Soil investigation for construction of one RCC Over Head Reservoir of staging height 20 Mtr. within command area of Mohanpur Water Supply Scheme in Barrackpore-II Block under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000031/2023-2024 | 639/NWSD-I | 26/05/2023 | 01/01/2027 | CONCORD ENGINEERING | 716.1 | 261.78 | 36.56 | 60
Total | [13 empty] | 991.75 | 362.97 | 36.6