## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Auldanga Zone-I W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000192/2021-2022 | 314/NWSD - I | 21/03/2022 | 28/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.3 | 4.3 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of Auldanga Zone-1 Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000047/2022-2023 | 875/NWSD-I | 22/07/2022 | 20/10/2022 | MONDAL ENTERPRISE | 259.06 | 256.45 | 98.99 | 85
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 881/NWSD-I | 22/07/2022 | 22/07/2022 | Resource Division | 79.88 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 1163/NWSD-I | 26/09/2022 | 26/09/2022 | Resource Division | 0.01 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Repair and renovation works of 700 m3 RCC Elevated Reservoir, Boundary Wall, Pump House, Service roads etc. at Head Works Site and other tube well Sites under AULDANGA ZONE-I Water Supply scheme in Bagdah Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000136/2022-2023 | 234/NWSD-I | 02/03/2023 | 01/05/2023 | ONKAR ENTERPRISE | 65.07 | 59.43 | 91.33 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Laying of distribution pipe line & Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete at Auldanga Zone -I W/S Scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000145/2023-2024 | 1511/NWSD-I | 22/09/2023 | 21/11/2023 | M/S. ASOKE GHOSH AND BROTHERS | 38.23 | 0 | 0 | 2
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I, II and III Zone-I Rep. under Auldanga WS Scheme District of 24 Pgs. North. WBPHED/EE/EMD/NIET-27/2022-2023 [SL.-2] | Assistant Engineer | Junior Engineer | ORD/003330/2023-2024 | 4758./EMD | 07/08/2023 | 06/09/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 39.72 | 23.06 | 58.06 | 60
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Renovation of AIRP at Auldanga Zone-I Water Supply Scheme of capacity 147.88 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000060/2024-2025 | 1668/NWSD-I | 19/11/2024 | 14/11/2025 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 109.3 | 0 | 0 | 60
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. | SM/10580 | Augmentation | Protection work & land development at H/W Site under Augmentation Scheme of Auldanga W/S Scheme (Zone - II) within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000071/2024-2025 | 54/NWSD-I | 09/01/2025 | 08/02/2025 | MONDAL ENTERPRISE | 45.44 | 0 | 0 | 0
Total | [13 empty] | 650.88 | 343.25 | 52.74