## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household with in Paschim Panchberia (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000125/2021-2022 | 1192/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.75 | 4.75 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVc, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Paschim Panchberia Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000054/2022-2023 | 967/NWSD-I | 12/08/2022 | 10/11/2022 | MADE & TRADE CO. | 412.72 | 415.86 | 100.76 | 100
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 44 m Length in 3rd. Pump house site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000153/2022-2023 | 280/NWSD-I | 14/03/2023 | 28/04/2023 | M/S DAS AND CO | 5.16 | 3.49 | 67.52 | 100
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Service Road (60 Mtr. Length X 3 Mtr. Width) at Headwork site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000155/2022-2023 | 282/NWSD-I | 14/03/2023 | 28/04/2023 | R K ENTERPRISE | 4.69 | 4.72 | 100.65 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Repair & Renovation for one no. Pump house at 3rd Tube well site and Service Road (25 Mtr. Length X 2 Mtr. Width) at 2nd & 3rd Tube well site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000156/2022-2023 | 283/NWSD-I | 14/03/2023 | 28/04/2023 | M/S. SUPER CONSTRUCTION | 5.72 | 5.34 | 93.45 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 44 m Length in 2nd Pump house site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000152/2022-2023 | 279/NWSD-I | 14/03/2023 | 28/04/2023 | A. S. ENTERPRISE | 5.19 | 3.77 | 72.76 | 100
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Special Repair & Renovation for two nos. (Head work site and 2nd Tube well site) Pump house and Allied Works as per site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000154/2022-2023 | 281/NWSD-I | 14/03/2023 | 28/04/2023 | M/S. SANDHYA CONSTRUCTION | 5.25 | 4.69 | 89.33 | 20
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Construction of BOUNDARY WALL for 167 m Length at Head work site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000020/2023-2024 | 492/NWSD-I | 26/04/2023 | 10/06/2023 | PHOENIX INFRASTRUCTURE | 19.93 | 19.28 | 96.77 | 15
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 970/NWSD-I | 12/08/2022 | 12/08/2022 | Resource Division | 43.47 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Renovation of AIRP at Paschim Pachneria Zone-I Water Supply Scheme of capacity 110.81 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000101/2024-2025 | 1738/NWSD-I | 28/11/2024 | 27/05/2025 | MONDAL PRECISION PRIVATE LIMITED | 63.45 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Laying of distribution pipe line at Paschim Pancberia Zone -I W/S Scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000106/2023-2024 | 1236/NWSD-I | 18/08/2023 | 17/10/2023 | A.K.C. SUPPLY & CONSTRUCTION | 63.24 | 62.17 | 98.32 | 100
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir of 550 cum at Paschim Panchberia Zone-I" of Bongon Block in the district of North 24 pargana(s) under North 24 Pgs. W/S Div-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000115/2023-2024 | 1265/NWSD-I | 21/08/2023 | 20/10/2023 | SAMBIT NEOGI | 14.05 | 12.78 | 90.99 | 30
13 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
14 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10581 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVc, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Paschim Panchberia Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. |  |  | BILL/00417/2025-2026 |  | 19/12/2025 | 19/12/2025 | MADE & TRADE CO. | 22.06 | 0 | 0 | 0
Total | [13 empty] | 674.27 | 536.86 | 79.62