## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Auldanga Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000193/2021-2022 | 315/NWSD - I | 21/03/2022 | 28/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.92 | 3.92 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 1211/NWSD-I | 13/10/2022 | 13/10/2022 | Resource Division | 7.42 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 454/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 55.56 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | Laying of Distribution System including specials & valves, pipe carrying structure, Providing FHTC including supplying , laying, fitting, fixing of 15 mm NB PVC (Schedule 80) / 20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun meter ferrule, saddle piece etc. all complete, construction works of R.C.C Elevated Reservoir 350m3,Construction of Pump House, Boundary wall, Service Road (25Mtr. Length x 2 Mtr. Width) at Pump House site at Auldanga Zone - II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000082/2023-2024 | 929/NWSD-I | 17/07/2023 | 17/07/2024 | MONDAL ENTERPRISE | 476.14 | 127.07 | 26.69 | 65
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0.14 | 2.65 | 100
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | New service connection at P.H.No- I ,Zone-II of Auldanga water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). Type : |  |  | BILL/05019/2023-2024 | BP-339-23-24 | 11/03/2024 | 11/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.11 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Central Drilling | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. | SM/10582 | Augmentation | Protection work & land development at H/W Site under Augmentation Scheme of Auldanga W/S Scheme (Zone - II) within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000071/2024-2025 | 54/NWSD-I | 09/01/2025 | 08/02/2025 | MONDAL ENTERPRISE | 45.44 | 0 | 0 | 0
Total | [13 empty] | 21941.63 | 131.13 | 0.6