## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Barakpur (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000133/2021-2022 | 1181/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.59 | 4.59 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Laying of Distribution pipe line and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system at distribution system within command area of Barakpur Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/000082/2022-2023 | 1354/NWSD-I | 28/11/2022 | 26/02/2023 | JOY HIND TUBEWELLS | 394.47 | 397.89 | 100.87 | 25
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Barakpur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001153/2023-2024 | 4756/EMD | 07/08/2023 | 06/09/2023 | SWAPAN KUMAR BHANJA | 26.67 | 15.8 | 59.26 | 80
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir of 900 Cum capacity at Head work site & other allied works of Barakpur (Zone-I) water supply scheme and other ancillary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000144/2023-2024 | 1393/NWSD-I | 05/09/2023 | 04/11/2023 | A.K.C. SUPPLY & CONSTRUCTION | 30.29 | 27.07 | 89.39 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 50 m Length & Service Road (25 Mtr. Length X 2 Mtr. Width) at 2nd pump house site at BARAKPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000018/2023-2024 | 446/NWSD-I | 25/04/2023 | 09/06/2023 | MONDAL ENTERPRISE | 7.28 | 5.9 | 80.98 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Special Repair and renovation works of Pump House, Boundary Wall & other allied works of Barakpur ( Zone-I) water supply scheme and other ancillary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000143/2023-2024 | 1392/NWSD-I | 05/09/2023 | 04/11/2023 | OM CONSTRUCTION | 20.63 | 17.14 | 83.11 | 100
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 469/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 54.61 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Construction of Arsenic cum Iron removal Plants (AIRP) of capacity 168 cum/hr at Head work site of Barakpur (Zone-1) Water Supply Scheme within the Bongaon Block and other ancillary work under North 24 Pgs. w/s Division-l, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000362/2023-2024 | 489/NWSD-I | 15/03/2024 | 12/09/2025 | EFFLUENT & WATER TREATMENT ENGINEERS(P) LTD. | 371.87 | 0 | 0 | 25
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-III & IV Zone-I under Barrakpur ground water based water supply scheme under Block_ Bongaon Dist. - North 24PGS under EMD, PHE Dte. | Assistant Engineer |  | ORD/000017/2024-2025 | 1309/EMD | 09/05/2024 | 08/06/2024 | A.S. ENTERPRISE | 26.08 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Repairing of GI Roofing, Structural works including finishing and other allied works at Sripally Barrackpore Store under North 24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000359/2023-2024 | 462/NWSD-I | 13/03/2024 | 27/03/2024 | OM CONSTRUCTION | 5.19 | 5.13 | 98.88 | 100
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 1306/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 6.16 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Laying of UPVC pipes at demage portion due to drain construction & protection work by Bullah pilling N/H of Jayanta Sandhu to Ranjit Chakraborty under Augmentation work of Barrakpur (Zone - I) W/S Scheme, Bongaon Block of North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000019/2025-2026 | 775/NWSD-I | 23/05/2025 | 07/07/2025 | OM CONSTRUCTION | 22.32 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Laying of pipeline & special measure for protection of road and other allied works at different location under Augmentation work at Barakpur Zone-I W/S. Scheme in Bongaon Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000072/2024-2025 | 53/NWSD-I | 09/01/2025 | 19/01/2026 | OM CONSTRUCTION | 19.66 | 0 | 0 | 100
15 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | SM/10583 | Augmentation | Laying of Distribution pipe line and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system at distribution system within command area of Barakpur Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. |  |  | BILL/00097/2025-2026 |  | 24/06/2025 | 24/06/2025 | JOY HIND TUBEWELLS | 21.22 | 0 | 0 | 0
Total | [13 empty] | 1016.31 | 473.53 | 46.59